## Sheet1
Timeline :- Inventory Check System
Start date: 15/09/2019 AND End Date: 22/05/2020
Task Name | Duration | Start Date | End Date | Comment
Project Plan |  | 2019-09-15 | 2019-11-01
➡ Project Blog (Setting Up) | 1 day | 2019-09-29 | 2019-09-30 | N/A
➡ Project Ideation | 10 days | 2019-09-20 | 2019-09-30 | N/A
➡ Market Research | 1 week | 2019-10-31 | 2019-11-07 | N/A
➡ Looking similar Project | 5 days | 2019-10-08 | 2019-10-13 | N/A
➡ Speaking to supervisor | 1 day | 2019-10-14 | 2019-10-15 | N/A
➡ Asking Friends | 2 days | 2019-10-16 | 2019-10-18 | N/A
➡ Research about the software | 2 days | 2019-10-19 | 2019-10-21 | N/A
➡ Project Specification | 10 days | 2019-10-22 | 2019-11-01 | N/A
Requirement Specification
➡ Interview Local Shops | 3 days | 2019-11-02 | 2019-11-05 | N/A
➡ Observing similar system | 1 week | 2019-11-07 | 2019-11-14 | N/A
➡ Create Gantt Chart | 4 days | 2019-11-15 | 2019-11-19 | N/A
➡ Wireframe | 2 days | 2019-11-20 | 2019-11-22 | N/A
➡ Break from this project to complete other module assignment | 3 weeks | 2019-11-23 | 2019-12-14 | N/A
➡ Interim Report | 2 weeks | 2019-12-15 | 2019-12-29 | This task has not been complete because of new year break.
| 1 week | 2019-12-30 | 2020-01-05 | Therefor it is been overdue by 1 week
Implementation
➡ Build the program | 9 weeks | 2020-01-06 | 2020-03-08 | N/A
➡ Draft Report | 18 days | 2020-03-09 | 2020-03-27 | N/A
➡ Test the program | 2 weeks | 2020-03-28 | 2020-04-11 | N/A
➡ Solve the Progarm if their is any during testing | 1 weeks | 2020-04-12 | 2020-04-19 | N/A
Review
➡ Ask friend to test the program | 2 days | 2020-04-20 | 2020-04-22 | N/A
Create Final Report | 29 days | 2020-04-23 | 2020-05-22 | N/A
END OF THE TIMELINE